## Strat 1-FS
Strategic Objective 1
Clinic Locator & Referral System: Fertility Scout 2.0
Strategy & Action Items |  | Team | Due | Status | Q1 | Q2 | Q3 | Q4 | Notes
Phase 1: Fertility Scout Redesign with Slolom
Planning & Redesign
| Remodel tool, removing referral capability/need for HIPAA servers | MB & JDR | 2021-12-31 | Completed
| Add new services; post-treatment in addition to FP | MB & JDR | 2021-12-31 | Completed
| Review and modify listings (addresses, clinic names, contact info) for mapping | MB & JDR | 2021-12-31 | Completed
| Enroll new clinics, businesses, and organizations, growing our network & providing additional patient resources | MB & JDR | 2021-12-31 | Completed
| Increase awareness & use of tool by creating new marketing collaterol (eg- promo video) | MB & JDR | 2021-12-31 | Completed
| Create funding mechanism- Membership Model | MB & JDR | 2021-12-31 | Completed
Manage Listings
| As clinics enroll, activate their referral capability | MB |  | Ongoing
| Troubleshoot tool issues with listers | MB |  | Ongoing
| Revise listings as needed/indicated clinic changes | MB |  | Ongoing
Phase 2: AFP Membership Recruitment
Recruit Participants: Part 1
| Identify "target" groups: ASRM, FPSIG, SART, Sperm banks | MB & JDR | 2021-12-31 | Completed
| Write text explaining system | MB & JDR | 2021-12-31 | Completed
| Draft outreach letter, blog | MB & JDR | 2021-12-31 | Completed
| Solicit listings (as needed) from important/leading centers | MB & JDR |  | Ongoing
| Follow up w/ all BOD members re: their institutions | MB & JDR | 2021-12-31 | Completed
| Review & approve outreach letter & blog | MB & JDR | 2021-12-31 | Completed
| Email/Mail letter to AFP membership | MB & JDR | 2021-12-31 | Completed
| Post blog (coordinate) | MB, JDR, JP | 2021-12-31 | Completed
Recruit Participants: Part 2- Enrollment Coordinator
| Share project descrioption with BOD for recruitment | MB & JDR | 2022-08-31 | Completed
| Review Applicants | MB & JDR | 2022-08-31 | Completed
| Onboard Enrollment Coordinator | MB & TBD | 2022-09-01
| Data Clean Up | AC
| Identify recruitment contacts at clinics | AC | 2022-12-31
| Develop recruitment script for cold calling | AC | 2022-12-31
| Identify other modes of recruitment outreach | AC | 2022-12-31
| Ensure membership clinics are successfully paid and enrolled | AC | 2022-12-31
| Enrollment Coordinator tracks recruitment | AC | 2022-12-31
| Identify Exective Team Large Networks | AC | 2022-12-31
| Evaluate success of Enrollment Coordinator | MB & JDR | 2022-12-31
| Organize Constant Contact | AC | 2022-02-28
| Evaluate CME Fertility Conference Potential | AC | 2022-02-28
| Evaluate Harness (round up) & Identify Retail Partners | AC | 2022-02-28
Phase 3: Promote Program to Oncology Community to Increase Utilization
Untertake Outreach
| Create "marketing" materials | MB & JDR
| Advocacy booth at ASCO | MB & JDR |  | Completed |  | X
| Outreach to prof groups: ASCO/QOPI, ONS, AOSW, COG & AYA orgs/programs | MB & JDR |  | Ongoing
| Outreach to network of cancer centers | MB & JDR
| Request linking/isting as a resource through cancer centers | MB & JDR
| Request linking/isting as a resource through other orgs websites | MB & JDR
Explore New Dissemination Channels
| Through MDACC decision aid | JDR | Q2
| Explore Teen Cancer America meeting/use of tool | JDR/MB
| Custom outreach to other AYA navigators | JDR